VAGT Security Services Pvt Ltd Est. 2017 · Bengaluru Master Brief Business context, decisions made, 6-month roadmap, and open questions. Version 1.0 · March 2026 · Confidential

# 1. Business Context

THE COMPANY

| Legal name | VAGT Security Services Pvt Ltd |
| --- | --- |
| Incorporated | 2017, Bengaluru, Karnataka |
| Revenue | ₹5 Crore+ annually |
| Headcount | ~150 trained personnel |
| Active clients | 13 engagements |
| Registered office | No. 86/2, Second Floor, Seegehalli, Kannamangala Post, Kadugodi, Whitefield, Bengaluru – 560 067 |
| Phone | +91 90089 77711 / +91 82172 10589 / +91 98453 72783 |
| Current website | vagtsecurityservices.com (being replaced) |
| New domain | vagtservices.com (GoDaddy) |

LEADERSHIP

| Founder / Current MD | Father (60 years old, technically capable, all-age-friendly systems required) |
| --- | --- |
| Incoming leader | Nikhil Kumar Jha — Electronics Engineer, 11+ years Indian Army, Senior Product Associate JP Morgan London. Currently based in Ashford, UK. Returning to India to take over. |
| Transition goal | Full handover within 6 months. Nikhil to run company at enterprise scale for 10+ years. |

CORE SERVICES

| Security Services | Manned guarding — corporate, residential, construction. G4S-trained leadership. |
| --- | --- |
| Facilities Management | End-to-end FM: MEP, HVAC, cleaning, BMS, soft services. |
| Intelligent Surveillance | AI-driven threat detection, LoRa mesh nodes. In development — Coming Soon. |

WHAT WORKS TODAY

- Employee benefits (functional)

- GST compliance (in order)

- 13 active client contracts generating ₹5Cr+ revenue

- Strong operational ground team of 150+

WHAT DOES NOT WORK TODAY

- No HR department or system — no payslips, no structured employee records

- No Finance department — profits not reinvested or managed strategically

- No Purchase / Inventory management

- No structured client database — client data scattered, no CRM

- Zero structured marketing — occasional LinkedIn posts only

- No digital advertising on any platform

- Company run as a family business (“lalla company”) — not enterprise-grade

THE CORE PROBLEM IN ONE SENTENCE VAGT has the revenue, the people, and the reputation to be a ₹50Cr+ company — but it is being operated like a ₹5Cr company. The systems, processes, and infrastructure are missing. Nikhil’s job is to build them.

# 2. The Big Picture Goal

Build VAGT into an enterprise-grade security and facilities business over the next 6 months, with systems that run without manual intervention and a foundation that supports the long-term ambition of a Security SaaS product.

THREE HORIZONS

| Horizon 1 (0–6 months) | Get the house in order. Internal systems: HR, Finance, Operations, CRM. Website live. Marketing engine started. |
| --- | --- |
| Horizon 2 (6–18 months) | Grow revenue. Structured client acquisition. Expand into higher-margin segments (IT parks, gated communities). Reach ₹20Cr+. |
| Horizon 3 (18–36 months) | Productise. Security SaaS — sell the internal systems built in Horizon 1 to other security companies in India. Internal first, market second. |

# 3. Website — Current Status

What has been built

| Technology | Static HTML/CSS. No framework, no CMS. Fast, free to host. |
| --- | --- |
| Pages | index.html, security.html, facilities.html, surveillance.html, about.html, contact.html |
| Hosting | GitHub Pages — repo: github.com/nikhiljha3105/vagt-website-2026 |
| Domain | vagtservices.com on GoDaddy — DNS not yet pointed at GitHub Pages |
| Design | Deep navy (#0D1F3C) + amber (#F5C400) + warm white (#F7F6F2). Left sidebar navigation. Mobile responsive. |
| Logo | Custom SVG shield: amber background, navy shield, VA/GT text. Consistent across all pages. |
| Key copy | Hero: “Bangalore’s security and facilities partner.” CTA: “Get a Free Site Assessment” |
| WhatsApp | Green WhatsApp button on homepage hero and contact page — direct link to +91 90089 77711 |
| Contact form | Simplified to 2 mandatory fields: Name + Phone/Email. Optional message. Form action not yet wired. |
| Clients shown | EY, SV Infra Holding Ltd, HatsOff Helicopter Training, DS-Max Sangam Pvt Ltd, BeeHive Co-Working Spaces + “20+ Clients” tile |
| Est. year | 2017 — shown in all footers. Stat: 9+ years established. |

PENDING WEBSITE TASKS

- Connect vagtservices.com domain — GoDaddy DNS: 4 A records + 1 CNAME pointing to GitHub Pages

- Wire contact form to Formspree (free) — Nikhil needs a Formspree account (formspree.io), takes 5 minutes

- Visual refinements — Nikhil to share screenshot so specific colour/layout issues can be fixed

- Real VAGT logo PNG — if an official logo file exists, replace the SVG recreation

- Photography — hero section currently uses CSS gradient; real site photos would dramatically improve credibility

- Employee portal + Client portal pages — sidebar links exist but pages do not yet

- Surveillance page — marked “Coming Soon”; content needs expanding when product is ready

# 4. The 6-Month Roadmap

Each phase builds on the previous. Do not jump phases. Internal systems come before external marketing.

| P1 Month 1 | Get the Digital House in Order Foundation infrastructure and basic tools |  |
| --- | --- | --- |
|  | DELIVERABLES - Website live on vagtservices.com with working contact form - Client database — all 13 clients in a structured spreadsheet (name, contact, contract value, renewal date, service type) - Guard roster spreadsheet — all 150 employees, contact, salary, deployment site, join date - Basic payslip template — compliant with Indian labour law, generatable per employee - GoDaddy DNS configured, HTTPS live | NEEDS FROM YOU - List of all 13 clients with contract details - Employee roster (name, salary, site) - Formspree account (5 min signup) - GoDaddy login for DNS changes |

| P2 Month 1–2 | HR & Payroll — Basic Every employee gets a payslip. Every month. |  |
| --- | --- | --- |
|  | DELIVERABLES - Payslip generator — input: employee data, output: PDF payslip per employee - Attendance tracking template (simple Excel or Google Sheet) - Offer letter template (standard format, legally compliant) - Leave management log - Employee ID system (VAGT-001 format) | NEEDS FROM YOU - Salary structure (basic + HRA + allowances breakdown) - Any existing payroll records, even rough - PF / ESI registration status |

| P3 Month 2–3 | Finance Basics — Visibility First Know where every rupee is going |  |
| --- | --- | --- |
|  | DELIVERABLES - Monthly P&L template — revenue per client, guard cost per site, gross margin - Invoice template (GST-compliant, professional) - Accounts receivable tracker — who owes what, since when - Budget vs. actuals dashboard - Expense categorisation (guard wages, training, transport, admin) | NEEDS FROM YOU - Last 3 months of bank statements (rough is fine) - GST registration details - Current invoicing method (WhatsApp? Email? Paper?) |

| P4 Month 3–4 | Client CRM + Marketing Engine Stop losing clients. Start acquiring new ones. |  |
| --- | --- | --- |
|  | DELIVERABLES - CRM in Google Sheets or Airtable: all 13 clients, renewal dates, upsell opportunities - Marketing one-pager for apartment complexes (based on research already done) - LinkedIn content calendar — 4 posts/month, topics identified - BAF (Bangalore Apartments Federation) membership application - WhatsApp broadcast list for existing clients (announcements, renewals) - Email newsletter template for client communications | NEEDS FROM YOU - Approve marketing one-pager content - LinkedIn company page access - Budget for BAF membership (₹10–20k/year) |

| P5 Month 4–5 | Operations — Modernise the Core Guards in the right place. Supervisors accountable. |  |
| --- | --- | --- |
|  | DELIVERABLES - Deployment tracker — which guard is at which site, what shift - Incident log template — standardised reporting for all sites - Supervisor check-in system (WhatsApp-based, zero cost) - Purchase & inventory log (uniforms, equipment, consumables) - SLA document template for new client contracts - Guard retention programme — basic career path, recognition system | NEEDS FROM YOU - Current deployment list (who is where) - Any existing incident reports to understand format - Uniform/equipment stock count |

| P6 Month 5–6 | SaaS Foundation — Design & Validate Productise what works internally. Find 3 pilot customers. |  |
| --- | --- | --- |
|  | DELIVERABLES - Document all internal systems built in P1–P5 as product features - Competitive analysis of security SaaS market in India - 3 pilot customer conversations (other Bangalore security companies) - Product spec: what a Security SaaS MVP looks like - Pricing model draft - Tech stack decision (build vs. configure existing tools) | NEEDS FROM YOU - Appetite for external investment or bootstrapped only? - 3 contacts at other security companies willing to give feedback - Tech budget for SaaS development (rough range) |

# 5. Market Intelligence — Bangalore Residential Security

Research completed March 2026. Full report available on request.

KEY NUMBERS

| Market size (India security services) | USD 8.7 billion in 2024, growing at 4.8–6% CAGR |
| --- | --- |
| Residential share of manned guarding | ~39% of all manned guarding in India |
| BAF member associations (Bangalore) | 1,247 apartment associations — the single best marketing channel |
| Industry guard attrition | 30–40% annually — VAGT’s biggest differentiator if reduced |
| Trained guard attrition (global) | 15% — achievable target for VAGT with basic retention programme |
| Residential guard pricing | ₹13,000–20,000/guard/month (what RWAs pay) |
| Gross margin (industry average) | 5–7% on residential. 10–15% on IT parks / gated communities. |
| Customer acquisition cost (referral-based) | ₹2,000–3,000 per contract vs. ₹5,000–8,000 via paid advertising |

STRATEGIC RECOMMENDATIONS (FROM RESEARCH)

- 1. Join BAF — 1,247 RWAs in one place. One membership fee, unlimited warm introductions.

- 2. Reduce attrition to 15–20% — this IS the product. Market it. “Our guards stay. Yours won’t keep changing.”

- 3. Price at ₹19,000–21,000/guard — above cheap local, below G4S. Justify on total cost of ownership.

- 4. Pursue IT parks and large gated communities in parallel — 10–15% margins vs. 5–7% for basic residential.

- 5. Facility Manager referral programme — ₹7,500 per successful referral. Target 500 FMs in Bangalore.

# 6. How to Work With Claude Effectively

From our first session — recorded here so every future session starts right.

WHAT WORKS

- Bring data, not descriptions. A spreadsheet of your 13 clients unlocks 10x more output than describing them in words.

- Give decisions, not problems. “Build me a payslip generator for 150 employees in Indian labour law format” is 10x better than “I don’t have payslips.”

- One phase at a time. Finish before moving. The website isn’t done until it’s live on vagtservices.com with a working form.

- Start every session by saying which Phase you’re working on and what you want to leave with. This brief handles the rest.

- Push back is productive. Claude will flag when something is wrong — engage with it, don’t skip it.

WHAT WASTES TIME

- Context-switching mid-task. Pick one thing and finish it.

- Vague requests (“make it better”). Be specific: “the amber is too bright on mobile” is actionable.

- Starting new sessions without referencing this brief. Always open with: “I’m on Phase X, I want to finish Y today.”

# 7. Open Questions — Blocking Progress

These need answers before the relevant phase can proceed. Review and fill in.

| Q1 | What is the correct email for vagtservices.com? Is info@vagtservices.com active? |
| --- | --- |
| Q2 | Does an official VAGT logo file (PNG/SVG) exist? The website currently uses a recreation. |
| Q3 | Is the contact phone number +91 90089 77711 the one you want WhatsApp enquiries on? |
| Q4 | Who is the point of contact for Formspree form submissions — your email or a VAGT email? |
| Q5 | What is the current invoicing / billing method for clients? |
| Q6 | Is PF / ESI registered for all 150 employees? |
| Q7 | What is the salary structure breakdown for guards (basic + HRA + allowances)? |
| Q8 | For the SaaS: bootstrapped or open to external investment? |
| Q9 | Budget for Phase 1–2 tooling (CRM, payroll software, etc.)? Preference for free tools or paid? |
| Q10 | Timeline pressure: when is Nikhil relocating to Bengaluru? |

This document is the single source of truth for the VAGT transformation project. Update it when decisions change. Reference it at the start of every session.